## Sprint 1
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
1 | As an inexperienced player, I want to know the rules of Rummy so that I can play the game. (the rules of Rummy vary wildly depending on who you ask) | Learn the rules of Rummy | 1 | Posess a deep understanding of how to play Rummy | NF: KA | 1 | 1
2 | As a User, I want to know what the controls are so that I can play the game | UI mockup | 1 | Controls are clear from UI | F | 1 | 1

## Sprint 2
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
4 | As a User, I want to see what cards are in my hand so I know what plays I can make. | Implement hand part of UI | 2 | Users should be able to easily tell what cards they have | F | 2 | 2
3 | As a User, I want to see what melds are on the board so I know which I can use. | Implement meld part of UI | 2 | Users should be able to quickly tell what melds are available | F | 2 | 2

## Sprint 3
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
5 | As a User, I want to know what the score is so I can play multiple rounds. | Implement score part of UI | 3 | Users should be able to quickly and easily tell what the score is | F | 2 | 1
12 | As a User, I want to know whether aces are high or low, so I can strategize better. | Implement aces high/low indicator UI | 3 | Users should be able to easily tell if aces are high or low | F | 2 | 1
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | Implement rearranging of cards in hand | 3 | Users should be able to re-organize their hand to their liking | F | 3 | 1