## Sprint 1
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
1 | As an inexperienced player, I want to know the rules of Rummy so that I can play the game. (the rules of Rummy vary wildly depending on who you ask) | Learn the rules of Rummy | 1 | Posess a deep understanding of how to play Rummy | NF: KA | 1 | 1
2 | As a User, I want to know what the controls are so that I can play the game | UI mockup | 1 | Controls are clear from UI | F | 1 | 1

## Sprint 2
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
4 | As a User, I want to see what cards are in my hand so I know what plays I can make. | Implement hand part of UI | 2 | Users should be able to easily tell what cards they have | F | 2 | 2
3 | As a User, I want to see what melds are on the board so I know which I can use. | Implement meld part of UI | 2 | Users should be able to quickly tell what melds are available | F | 2 | 2