## Sprint 1
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
1 | As an inexperienced player, I want to know the rules of Rummy so that I can play the game. (the rules of Rummy vary wildly depending on who you ask) | Learn the rules of Rummy | 1 | Posess a deep understanding of how to play Rummy | NF: KA | 1 | 1
2 | As a User, I want to know what the controls are so that I can play the game | UI mockup | 1 | Controls are clear from UI | F | 1 | 1

## Sprint 2
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
4 | As a User, I want to see what cards are in my hand so I know what plays I can make. | Implement hand part of UI | 2 | Users should be able to easily tell what cards they have | F | 2 | 2
3 | As a User, I want to see what melds are on the board so I know which I can use. | Implement meld part of UI | 2 | Users should be able to quickly tell what melds are available | F | 2 | 2

## Sprint 3
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed
5 | As a User, I want to know what the score is so I can play multiple rounds. | Implement score part of UI | 3 | Users should be able to quickly and easily tell what the score is | F | 2 | 1
12 | As a User, I want to know whether aces are high or low, so I can strategize better. | Implement aces high/low indicator UI | 3 | Users should be able to easily tell if aces are high or low | F | 2 | 1
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | Implement rearranging of cards in hand | 3 | Users should be able to re-organize their hand to their liking | F | 3 | 1

## Sprint 4
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Contributor(s)
5 | As a User, I want to know what the score is so I can play multiple rounds. | Implement score part of UI | 3,4,5 | Users should be able to quickly and easily tell what the score is | F | 2 | 1 | Gunnar Eastman, Kion Tupper
12 | As a User, I want to know whether aces are high or low, so I can strategize better. | Implement aces high/low indicator UI | 3,4 | Users should be able to easily tell if aces are high or low | F | 2 | 2 | Matthew Virgin
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | Implement rearranging of cards in hand | 3,4,5 | Users should be able to re-organize their hand to their liking | F | 3 | 1 | Kion Tupper
14 | As an impatient person, I want to be able to start over so that I won’t have to finish games with poor hands. | Implement resetting the game | 4,5 | Users should be able to restart if they don't like how their game is going | F | 1 | 0.5 | Kion Tupper
9 | As a User, I want to know why the play I tried to make was illegal so that I can inform myself and improve my play. | Implement help page/rules | 4 | Users should be able to learn as they play or before | F | 1 | 1 | Matthew Virgin
18 | As a User, I want the UI to be color coded so that it is easy for me to understand what the app can do. | Add color coordination to UI buttons | 4 | Users should be able to tell buttons apart quickly and easily | F | 2 | 2 | Kion Tupper

## Sprint 5
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Contributor(s)
5 | As a User, I want to know what the score is so I can play multiple rounds. | Implement score part of UI | 3,4,5,6 | Users should be able to quickly and easily tell what the score is | F | 2 | 1 | Gunnar Eastman, Kion Tupper
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | Implement rearranging of cards in hand | 3,4,5,6 | Users should be able to re-organize their hand to their liking | F | 3 | 1 | Kion Tupper
14 | As an impatient person, I want to be able to start over so that I won’t have to finish games with poor hands. | Implement resetting the game | 4,5 | Users should be able to restart if they don't like how their game is going | F | 1 | 1(you can just refresh the page) | Kion Tupper
15 | As a User, I want to be able to customize the background to make it more visually appealing so that I can express myself. | Implement background color editing | 5 | Users should be able to change the background color to their liking | F | 2 | 2 | Matthew Virgin
10 | As a busy person, I want the option of playing against AI, so I can play whenever I want. | Make game playable | 5,6 | The game should beplayable for testing | F | 2 | 1 | Kion Tupper
16 | As an artistic player, I want to be able to customize the deck used so that I feel more attached to the game. | Implement card color customization | 5 | Users should be able to customize the color of their cards to their liking | F | 2 | 2 | Matthew Virgin

## Sprint 6
ID | Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Contributor(s)
5 | As a User, I want to know what the score is so I can play multiple rounds. | Implement score part of UI | 3,4,5,6 | Users should be able to quickly and easily tell what the score is | F | 2 | 2 | Gunnar Eastman, Kion Tupper
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | Implement rearranging of cards in hand | 3,4,5,6,6+ | Users should be able to re-organize their hand to their liking | F | 3 | 1 | Kion Tupper
10 | As a busy person, I want the option of playing against AI, so I can play whenever I want. | Make game playable | 5,6 | The game should beplayable for testing | F | 2 | 2 | Kion Tupper
8 | As a User, I want myself and others to be prevented from making illegal plays, so that the game can run fairly. | Prevent illegal moves during gameplay | 6 | Cheating should not be a possibility in the same way it is in a normal card game | F | 3 | 3 | Kion Tupper
11 | As a social player, I want the option of playing against my friends, so I can have fun in a group. | Implement multiplayer between real people | 6,6+ | Players should be able to join each other's games | F | 2 | 2 | Kion Tupper
19 | As a User, I want to change the colors of the suits so I can tell them apart better. | Allow users to change suit colors | 6 | There should be at least 1 alternate set of suit colors | F | 2 | 2 | Matthew Virgin
17 | As a competitive player, I want to be able to adjust the number of AI players for a more chaotic experience. | Allow users to add more AI opponents | 6,6+ | Users should be able to play against up to 3 other enemy AI | F | 3 | 3 | Kion Tupper
6 | As a User, I want to modify the rules to use more or fewer decks of cards so that I can play how I want. | Allow users to add/remove decks used | 6,6+ | Users should be able to change the number of decks the game uses | F | 3 | 3 | Kion Tupper
7 | As a creative player, I want to be able to modify the rules so that the game is more interesting for myself and others. | Allow users to modify several rules of the game | 6,6+ | Users should be able to modify other parts of the game, like using jokers, aces high/low | F | 3 | 3 | Kion Tupper