## Product Backlog
ID | Story | Story Priority | Sprint Number | Story Status | Story Points
1 | As an inexperienced player, I want to know the rules of Rummy so that I can play the game. (the rules of Rummy vary wildly depending on who you ask) | H | 1 | W | 1
2 | As a User, I want the controls to be clear so that I can play rummy just as effectively as I could with a real deck of cards. | H | 1 | W | 1
4 | As a User, I want to see what cards are in my hand so I know what plays I can make. | H | 2 | W | 2
3 | As a User, I want to see what melds are on the board so I know which I can use. | H | 2 | W | 2
10 | As a busy person, I want the option of playing against AI, so I can play whenever I want. | H | 3 | W | 2
5 | As a User, I want to know what the score is so I can play multiple rounds. | M | 3 | W | 2
12 | As a User, I want to know whether aces are high or low, so I can strategize better. | M | 3 | W | 2
13 | As a User, I want to organize the cards in my hand to make them easier to look through so that I don’t get overwhelmed while playing. | M | 4 | W | 3
14 | As an impatient person, I want to be able to start over so that I won’t have to finish games with poor hands. | L | 4 | W | 1
9 | As a User, I want to know why the play I tried to make was illegal so that I can inform myself and improve my play. | L | 4 | W | 1
11 | As a social player, I want the option of playing against my friends, so I can have fun in a group. | H | 5 | W | 2
8 | As a User, I want myself and others to be prevented from making illegal plays, so that the game can run fairly. | H | 5 | W | 3
18 | As a User, I want the UI to be color coded so that it is easy for me to understand what the app can do. | L | 5 | W | 2
19 | As a User, I want to change the colors of the suits so I can tell them apart better. | L | 5 | W | 2
17 | As a competitive player, I want to be able to adjust the number of AI players for a more chaotic experience. | M | 6 | W | 3
15 | As a User, I want to be able to customize the background to make it more visually appealing so that I can express myself. | L | 6 | W | 2
16 | As an artistic player, I want to be able to customize the deck used so that I feel more attached to the game. | L | 6 | W | 2
6 | As a User, I want to modify the rules to use more or fewer decks of cards so that I can play how I want. | M | 6+ | W | 3
7 | As a creative player, I want to be able to modify the rules so that the game is more interesting for myself and others. | M | 6+ | W | 3
20 | As a User, I want to be able to save the state of my game and come back to it later so that I don’t have to clear my schedule to play a game. | M | 6+ | W | 3